## All
Phase No | Phase Name | Story | Sub-Task | Story Points
1 | Requirements and Research | Requirements Gathering | Define interview questions | 3
1 | Requirements and Research | Requirements Gathering | Conduct stakeholder interviews | 5
1 | Requirements and Research | Requirements Gathering | Analyze gathered requirements | 3
1 | Requirements and Research | Requirements Documentation | Create user story templates | 2
1 | Requirements and Research | Requirements Documentation | Document user stories or use cases | 3
1 | Requirements and Research | Competitor Analysis | Identify key competitors | 2
1 | Requirements and Research | Competitor Analysis | Analyze competitor APIs | 3
1 | Requirements and Research | Competitor Analysis | Document competitive features | 2
2 | High-Level Design | High-Level Architecture Proposal | Create architectural diagram | 5
2 | High-Level Design | High-Level Architecture Proposal | Define major components | 3
2 | High-Level Design | High-Level Architecture Proposal | Document architectural decisions | 4
2 | High-Level Design | Design Review Meeting | Schedule design review meeting | 2
2 | High-Level Design | Design Review Meeting | Prepare presentation materials | 3
2 | High-Level Design | Design Review Documentation | Document feedback and decisions | 3
3 | Detailed Design | Component Design - Authentication | Design authentication APIs | 4
3 | Detailed Design | Component Design - Authentication | Implement authentication security | 5
3 | Detailed Design | Component Design - Authentication | Document authentication design | 3
3 | Detailed Design | Component Design - Data Models | Define data models and schemas | 4
3 | Detailed Design | Component Design - Data Models | Document data model design | 3
3 | Detailed Design | Component Design - Data Models | Review data model design | 2
4 | Development | Development Environment Setup | Install necessary development tools | 3
4 | Development | Development Environment Setup | Configure development environments | 4
4 | Development | Coding - Authentication Component | Implement authentication component | 8
4 | Development | Coding - Authentication Component | Write unit tests for authentication | 4
4 | Development | Coding - Authentication Component | Integrate authentication into the API | 6
4 | Development | Coding - Data Models | Implement data models and schemas | 6
4 | Development | Coding - Data Models | Write unit tests for data models | 4
4 | Development | Coding - Data Models | Integrate data models into the API | 5
5 | Code Review | Code Review Meeting | Schedule code review meetings | 2
5 | Code Review | Code Review Meeting | Invite relevant team members | 3
5 | Code Review | Code Review Meeting | Conduct code review sessions | 4
5 | Code Review | Code Review Documentation | Document code review feedback | 3
5 | Code Review | Code Review Documentation | Track code review issues | 2
5 | Code Review | Code Review Documentation | Identify code quality improvements | 3
6 | Testing | Unit Testing - Authentication | Write unit tests for authentication component | 4
6 | Testing | Unit Testing - Authentication | Execute unit tests for authentication | 4
6 | Testing | Unit Testing - Authentication | Address unit test failures | 3
6 | Testing | Unit Testing - Data Models | Write unit tests for data models | 4
6 | Testing | Unit Testing - Data Models | Execute unit tests for data models | 4
6 | Testing | Unit Testing - Data Models | Resolve unit test failures | 3
6 | Testing | Integration Testing | Plan integration testing scenarios | 4
6 | Testing | Integration Testing | Execute integration tests | 5
6 | Testing | Integration Testing | Address integration test failures | 4
6 | Testing | End-to-End Testing | Create end-to-end test cases | 5
6 | Testing | End-to-End Testing | Execute end-to-end tests | 6
6 | Testing | End-to-End Testing | Manage feedback from stakeholders | 7
7 | Documentation | API Documentation | Create API documentation outline | 3
7 | Documentation | API Documentation | Document API endpoints and methods | 5
7 | Documentation | API Documentation | Provide usage examples and code snippets | 4
8 | Security Review | Security Assessment | Schedule security review | 3
8 | Security Review | Security Assessment | Conduct security assessment | 4
8 | Security Review | Security Assessment | Identify and document vulnerabilities | 4
8 | Security Review | Security Issue Remediation | Plan and prioritize security issue fixes | 3
8 | Security Review | Security Issue Remediation | Implement security fixes | 4
8 | Security Review | Security Issue Remediation | Document resolved security issues | 3
9 | Performance Optimization | Performance Testing | Plan performance testing scenarios | 4
9 | Performance Optimization | Performance Testing | Execute performance tests | 6
9 | Performance Optimization | Performance Testing | Optimize code based on test results | 5
10 | User Acceptance Testing (UAT) | UAT Planning | Plan UAT scenarios and criteria | 4
10 | User Acceptance Testing (UAT) | UAT Planning | Schedule UAT sessions | 3
10 | User Acceptance Testing (UAT) | UAT Execution | Conduct UAT sessions | 5
10 | User Acceptance Testing (UAT) | UAT Execution | Document UAT feedback and issues | 5
11 | Release Preparation | Versioning Strategy | Decide on API versioning strategy | 3
11 | Release Preparation | Versioning Strategy | Implement versioning in the API | 4
11 | Release Preparation | Tagging and Branching | Create release tags or branches | 2
11 | Release Preparation | Tagging and Branching | Document release versioning | 2
12 | Deployment | Deployment Plan | Create a deployment plan | 5
12 | Deployment | Deployment Plan | Execute the deployment plan | 6
12 | Deployment | Deployment Plan | Document deployment steps | 4
13 | Post-Release Support | Monitoring Setup | Set up monitoring tools | 4
13 | Post-Release Support | Monitoring Setup | Configure alerts and notifications | 3
13 | Post-Release Support | Monitoring Setup | Monitor API performance | 4
13 | Post-Release Support | Bug Fixes and Improvements | Handle and document post-release issues | 5
13 | Post-Release Support | Bug Fixes and Improvements | Implement bug fixes and improvements | 6
13 | Post-Release Support | Documentation Update | Update API documentation post-release | 3
14 | Retrospective | Retrospective Meeting | Conduct a project retrospective | 2
14 | Retrospective | Retrospective Meeting | Identify areas for process improvement | 3

## Requirements and Research
Phase | Story | Sub-Task | Story Points
Requirements and Research | Requirements Gathering | Define interview questions | 3
Requirements and Research | Requirements Gathering | Conduct stakeholder interviews | 5
Requirements and Research | Requirements Gathering | Analyze gathered requirements | 3
Requirements and Research | Requirements Gathering | Create user personas | 4
Requirements and Research | Requirements Gathering | Identify user stories | 5
Requirements and Research | Requirements Gathering | Document functional requirements | 6
Requirements and Research | Requirements Gathering | Document non-functional requirements | 4
Requirements and Research | Requirements Gathering | Prioritize requirements | 3
Requirements and Research | Requirements Gathering | Review requirements with stakeholders | 4
Requirements and Research | Requirements Gathering | Refine requirements based on feedback | 3
Requirements and Research | Requirements Documentation | Create user story templates | 2
Requirements and Research | Requirements Documentation | Document user stories or use cases | 3
Requirements and Research | Requirements Documentation | Define acceptance criteria | 2
Requirements and Research | Requirements Documentation | Validate requirements with stakeholders | 3
Requirements and Research | Requirements Documentation | Review and finalize documentation | 2
Requirements and Research | Requirements Documentation | Generate requirement traceability matrix | 4
Requirements and Research | Competitor Analysis | Identify key competitors | 2
Requirements and Research | Competitor Analysis | Analyze competitor APIs | 3
Requirements and Research | Competitor Analysis | Document competitive features | 2
Requirements and Research | Competitor Analysis | Identify gaps and opportunities | 3
Requirements and Research | Competitor Analysis | Summarize competitor analysis findings | 2
Requirements and Research | Market Research | Analyze market trends | 3
Requirements and Research | Market Research | Identify target audience | 2
Requirements and Research | Market Research | Assess market demand for the API | 4
Requirements and Research | Market Research | Document market research findings | 3
Requirements and Research | Regulatory Compliance | Research industry regulations | 4
Requirements and Research | Regulatory Compliance | Identify compliance requirements | 3
Requirements and Research | Regulatory Compliance | Document compliance strategies | 2
Requirements and Research | Regulatory Compliance | Review compliance with legal team | 4
Requirements and Research | User Surveys | Create user survey questions | 3
Requirements and Research | User Surveys | Distribute user surveys | 2
Requirements and Research | User Surveys | Collect and analyze survey responses | 4
Requirements and Research | User Surveys | Incorporate user feedback into requirements | 3
Requirements and Research | User Surveys | Summarize survey results | 2
Requirements and Research | Prototype Development | Create low-fidelity prototypes | 4
Requirements and Research | Prototype Development | Gather feedback on prototypes | 3
Requirements and Research | Prototype Development | Iterate on prototypes | 4
Requirements and Research | Prototype Development | Develop high-fidelity prototypes | 5
Requirements and Research | Prototype Development | Review prototypes with design team | 3
Requirements and Research | Use Case Scenarios | Define common use case scenarios | 3
Requirements and Research | Use Case Scenarios | Create user flow diagrams | 4
Requirements and Research | Use Case Scenarios | Identify edge case scenarios | 2
Requirements and Research | Use Case Scenarios | Document use case scenarios | 3
Requirements and Research | Use Case Scenarios | Review use cases with product owner | 3
Requirements and Research | Technical Feasibility Study | Assess technical feasibility of the project | 5
Requirements and Research | Technical Feasibility Study | Identify technical challenges | 4
Requirements and Research | Technical Feasibility Study | Document technical feasibility report | 3
Requirements and Research | Technical Feasibility Study | Review report with development team | 2
Requirements and Research | Data Requirements | Define data sources and data needs | 4
Requirements and Research | Data Requirements | Analyze data availability | 3
Requirements and Research | Data Requirements | Document data requirements | 3
Requirements and Research | Data Requirements | Review data requirements with data team | 2
Requirements and Research | Performance Requirements | Define performance objectives | 4
Requirements and Research | Performance Requirements | Analyze performance constraints | 3
Requirements and Research | Performance Requirements | Document performance requirements | 3
Requirements and Research | Performance Requirements | Review performance requirements with performance engineers | 2
Requirements and Research | Scalability Requirements | Identify scalability needs | 3
Requirements and Research | Scalability Requirements | Analyze potential bottlenecks | 4
Requirements and Research | Scalability Requirements | Document scalability requirements | 3
Requirements and Research | Scalability Requirements | Review scalability requirements with infrastructure team | 2
Requirements and Research | Security Requirements | Define security requirements | 4
Requirements and Research | Security Requirements | Analyze security risks | 4
Requirements and Research | Security Requirements | Document security requirements | 3
Requirements and Research | Security Requirements | Review security requirements with security experts | 3
Requirements and Research | Documentation Standards | Establish documentation standards | 2
Requirements and Research | Documentation Standards | Create a style guide | 2
Requirements and Research | Documentation Standards | Review documentation standards with documentation team | 2
Requirements and Research | Documentation Standards | Document documentation standards | 2
Requirements and Research | Compliance Requirements | Identify compliance standards | 3
Requirements and Research | Compliance Requirements | Review compliance requirements with legal team | 3
Requirements and Research | Compliance Requirements | Document compliance strategy | 2
Requirements and Research | Compliance Requirements | Review compliance strategy with compliance experts | 2
Requirements and Research | Localization Requirements | Define localization needs | 3
Requirements and Research | Localization Requirements | Analyze language and cultural requirements | 3
Requirements and Research | Localization Requirements | Document localization requirements | 2
Requirements and Research | Localization Requirements | Review localization requirements with localization experts | 2
Requirements and Research | API Dependencies | Identify third-party API dependencies | 3
Requirements and Research | API Dependencies | Analyze integration points | 3
Requirements and Research | API Dependencies | Document API integration requirements | 2
Requirements and Research | API Dependencies | Review integration requirements with integration team | 2
Requirements and Research | Quality Assurance Requirements | Define QA testing needs | 3
Requirements and Research | Quality Assurance Requirements | Analyze test coverage requirements | 3
Requirements and Research | Quality Assurance Requirements | Document QA testing requirements | 2
Requirements and Research | Quality Assurance Requirements | Review QA requirements with QA team | 2
Requirements and Research | Documentation Review | Review all requirements documentation | 3
Requirements and Research | Documentation Review | Incorporate feedback and revisions | 2
Requirements and Research | Documentation Review | Finalize requirements documentation | 2
Requirements and Research | Requirements Presentation | Prepare a presentation for stakeholders | 3
Requirements and Research | Requirements Presentation | Conduct a requirements review meeting | 4
Requirements and Research | Requirements Presentation | Address questions and feedback | 2
Requirements and Research | Requirements Presentation | Document meeting outcomes | 2
Requirements and Research | Requirements Sign-Off | Seek formal sign-off from stakeholders | 3
Requirements and Research | Requirements Sign-Off | Document signed-off requirements | 2
Requirements and Research | Requirements Sign-Off | File requirements documentation for reference | 2
Requirements and Research | Risk Assessment | Identify project risks | 3
Requirements and Research | Risk Assessment | Analyze potential impact of risks | 4
Requirements and Research | Risk Assessment | Document risk mitigation strategies | 3
Requirements and Research | Project Plan | Create a project plan for the
288

## High-Level Design
Phase | Story | Sub-Task | Story Points
High-Level Design | High-Level Architecture Proposal | Create architectural diagrams | 8
High-Level Design | High-Level Architecture Proposal | Define major components | 5
High-Level Design | High-Level Architecture Proposal | Document architectural decisions | 6
High-Level Design | High-Level Architecture Proposal | Review architecture with stakeholders | 4
High-Level Design | High-Level Architecture Proposal | Incorporate feedback into architecture | 5
High-Level Design | High-Level Architecture Proposal | Validate architecture with prototype | 6
High-Level Design | High-Level Architecture Proposal | Finalize architectural diagrams | 4
High-Level Design | High-Level Architecture Proposal | Document architectural rationale | 4
High-Level Design | High-Level Architecture Proposal | Present architecture to the team | 3
High-Level Design | Component Specification | Define specifications for each major component | 5
High-Level Design | Component Specification | Create component interface documentation | 4
High-Level Design | Component Specification | Review specifications with development team | 3
High-Level Design | Component Specification | Incorporate development team feedback | 4
High-Level Design | Component Specification | Document finalized component specifications | 3
High-Level Design | Component Specification | Review specifications with stakeholders | 3
High-Level Design | Component Specification | Validate specifications with prototype | 4
High-Level Design | Component Specification | Present component specs to the team | 2
High-Level Design | Technology Stack Selection | Identify suitable technologies for the project | 6
High-Level Design | Technology Stack Selection | Analyze pros and cons of each technology | 5
High-Level Design | Technology Stack Selection | Recommend the technology stack | 4
High-Level Design | Technology Stack Selection | Review technology recommendations with stakeholders | 3
High-Level Design | Technology Stack Selection | Document the chosen technology stack | 3
High-Level Design | Technology Stack Selection | Create a technology stack roadmap | 4
High-Level Design | Technology Stack Selection | Present technology stack to the team | 2
High-Level Design | Data Flow Diagrams | Create data flow diagrams for major components | 6
High-Level Design | Data Flow Diagrams | Review data flow diagrams with stakeholders | 4
High-Level Design | Data Flow Diagrams | Incorporate feedback into diagrams | 4
High-Level Design | Data Flow Diagrams | Document finalized data flow diagrams | 3
High-Level Design | Data Flow Diagrams | Validate data flow with prototype | 5
High-Level Design | Data Flow Diagrams | Present data flow diagrams to the team | 2
High-Level Design | Database Schema Design | Design the database schema | 7
High-Level Design | Database Schema Design | Review schema design with DBAs | 4
High-Level Design | Database Schema Design | Incorporate DBA recommendations | 4
High-Level Design | Database Schema Design | Document the finalized database schema | 3
High-Level Design | Database Schema Design | Validate schema design with prototype | 5
High-Level Design | Database Schema Design | Present schema design to the team | 2
High-Level Design | External API Integration | Identify external APIs for integration | 6
High-Level Design | External API Integration | Define integration points and methods | 5
High-Level Design | External API Integration | Review integration approach with external providers | 4
High-Level Design | External API Integration | Document the external API integration plan | 3
High-Level Design | External API Integration | Create API contracts for integration | 4
High-Level Design | External API Integration | Validate integration plan with prototype | 5
High-Level Design | External API Integration | Present integration plan to the team | 2
High-Level Design | Authentication Design | Design the authentication mechanism | 5
High-Level Design | Authentication Design | Review authentication design with security team | 4
High-Level Design | Authentication Design | Incorporate security recommendations | 4
High-Level Design | Authentication Design | Document the finalized authentication design | 3
High-Level Design | Authentication Design | Validate authentication design with prototype | 4
High-Level Design | Authentication Design | Present authentication design to the team | 2
High-Level Design | Error Handling Strategy | Define error handling and error codes | 4
High-Level Design | Error Handling Strategy | Review error handling approach with development team | 3
High-Level Design | Error Handling Strategy | Incorporate development team feedback | 3
High-Level Design | Error Handling Strategy | Document the finalized error handling strategy | 2
High-Level Design | Error Handling Strategy | Validate error handling with prototype | 3
High-Level Design | Error Handling Strategy | Present error handling strategy to the team | 2
High-Level Design | Logging and Monitoring | Design logging and monitoring mechanisms | 5
High-Level Design | Logging and Monitoring | Review logging and monitoring design with operations team | 4
High-Level Design | Logging and Monitoring | Incorporate operations team feedback | 4
High-Level Design | Logging and Monitoring | Document the finalized logging and monitoring plan | 3
High-Level Design | Logging and Monitoring | Validate logging and monitoring with prototype | 4
High-Level Design | Logging and Monitoring | Present logging and monitoring plan to the team | 2
High-Level Design | Scalability and Load Testing | Identify scalability requirements | 6
High-Level Design | Scalability and Load Testing | Design load testing scenarios | 5
High-Level Design | Scalability and Load Testing | Review load testing plan with performance team | 4
High-Level Design | Scalability and Load Testing | Document the load testing plan | 3
High-Level Design | Scalability and Load Testing | Create test data for load testing | 4
High-Level Design | Scalability and Load Testing | Validate load testing plan with prototype | 5
High-Level Design | Scalability and Load Testing | Present load testing plan to the team | 2
High-Level Design | Deployment Architecture | Design the deployment architecture | 6
High-Level Design | Deployment Architecture | Review deployment architecture with DevOps team | 5
High-Level Design | Deployment Architecture | Incorporate DevOps recommendations | 4
High-Level Design | Deployment Architecture | Document the finalized deployment architecture | 3
High-Level Design | Deployment Architecture | Validate deployment architecture with prototype | 4
High-Level Design | Deployment Architecture | Present deployment architecture to the team | 2
High-Level Design | Documentation Strategy | Define documentation requirements | 4
High-Level Design | Documentation Strategy | Identify documentation tools and templates | 3
High-Level Design | Documentation Strategy | Review documentation approach with documentation team | 3
High-Level Design | Documentation Strategy | Incorporate documentation team feedback | 3
High-Level Design | Documentation Strategy | Document finalized documentation strategy | 2
High-Level Design | Documentation Strategy | Present documentation strategy to the team | 2
High-Level Design | Review and Sign-Off | Schedule design review and sign-off meetings | 2
High-Level Design | Review and Sign-Off | Prepare presentation materials | 3
High-Level Design | Review and Sign-Off | Conduct design review meeting | 4
High-Level Design | Review and Sign-Off | Document design review feedback | 3
High-Level Design | Review and Sign-Off | Obtain sign-off from stakeholders | 3
High-Level Design | Review and Sign-Off | Validate sign-off with prototype | 3
High-Level Design | Review and Sign-Off | Finalize design documentation | 4
High-Level Design | Review and Sign-Off | Present design to the team | 2
High-Level Design | Quality Assurance Planning | Define QA testing needs | 4
High-Level Design | Quality Assurance Planning | Analyze test coverage requirements | 3
High-Level Design | Quality Assurance Planning | Review QA strategy with QA team | 3
High-Level Design | Quality Assurance Planning | Incorporate QA team feedback | 3
High-Level Design | Quality Assurance Planning | Document QA test plans | 3
High-Level Design | Quality Assurance Planning | Present QA plans to the team | 2
High-Level Design | Security Review Planning | Identify security requirements | 4
High-Level Design | Security Review Planning | Review security approach with security team | 3
High-Level Design | Security Review Planning | Incorporate security team recommendations | 3
High-Level Design | Security Review Planning | Document security review plans | 3
High-Level Design | Security Review Planning | Present security review plans to the team | 2
High-Level Design | Performance Testing Planning | Identify performance testing needs | 4
High-Level Design | Performance Testing Planning | Review performance testing approach with performance team | 3
High-Level Design | Performance Testing Planning | Incorporate performance team recommendations | 3
High-Level Design | Performance Testing Planning | Document performance testing plans | 3
High-Level Design | Performance Testing Planning | Present performance testing plans to the team | 2
High-Level Design | Scalability Assessment Planning | Identify scalability assessment needs | 4
High-Level Design | Scalability Assessment Planning | Review scalability assessment approach with team | 3
High-Level Design | Scalability Assessment Planning | Incorporate team recommendations | 3
High-Level Design | Scalability Assessment Planning | Document scalability assessment plans | 3
High-Level Design | Scalability Assessment Planning | Present scalability assessment plans to the team | 2
396

## Detailed Design - Component Des
Phase | Story | Sub-Task | Story Points
Detailed Design - Component Design | Component A Design | 1.1. Meet with the product owner to gather design requirements | 3
Detailed Design - Component Design | Component A Design | 1.2. Identify key stakeholders for design discussions | 2
Detailed Design - Component Design | Component A Design | 1.3. Review existing documentation and user stories | 2
Detailed Design - Component Design | Component A Design | 1.4. Conduct user interviews to understand user needs | 3
Detailed Design - Component Design | Component A Design | 1.5. Analyze user stories and functional requirements | 3
Detailed Design - Component Design | Component A Design | 1.6. Define design objectives and success criteria | 2
Detailed Design - Component Design | Component A Design | 2.1. Conduct a brainstorming session with the team to generate design ideas | 3
Detailed Design - Component Design | Component A Design | 2.2. Invite cross-functional team members for diverse input | 2
Detailed Design - Component Design | Component A Design | 2.3. Use whiteboards and collaborative tools for idea generation | 2
Detailed Design - Component Design | Component A Design | 2.4. Encourage team members to share innovative ideas | 3
Detailed Design - Component Design | Component A Design | 2.5. Select the most promising design concepts | 2
Detailed Design - Component Design | Component A Design | 3.1. Create initial sketches and wireframes for the component | 3
Detailed Design - Component Design | Component A Design | 3.2. Utilize wireframing tools for rapid prototyping | 2
Detailed Design - Component Design | Component A Design | 3.3. Incorporate user feedback into early designs | 3
Detailed Design - Component Design | Component A Design | 3.4. Iterate on wireframes based on feedback | 2
Detailed Design - Component Design | Component A Design | 3.5. Ensure wireframes align with user stories | 2
Detailed Design - Component Design | Component A Design | 4.1. Refine sketches based on feedback from team members | 3
Detailed Design - Component Design | Component A Design | 4.2. Engage in collaborative design reviews | 2
Detailed Design - Component Design | Component A Design | 4.3. Incorporate the team's input on usability and feasibility | 3
Detailed Design - Component Design | Component A Design | 4.4. Update sketches to address design concerns | 2
Detailed Design - Component Design | Component A Design | 4.5. Ensure sketches align with component requirements | 2
Detailed Design - Component Design | Component A Design | 5.1. Define data structures and data flow for the component | 4
Detailed Design - Component Design | Component A Design | 5.2. Identify data sources and data sinks | 2
Detailed Design - Component Design | Component A Design | 5.3. Map data flow between system components | 3
Detailed Design - Component Design | Component A Design | 5.4. Specify data validation and transformation rules | 3
Detailed Design - Component Design | Component A Design | 5.5. Document data schema and relationships | 3
Detailed Design - Component Design | Component A Design | 6.1. Specify API endpoints methods and request/response structures | 4
Detailed Design - Component Design | Component A Design | 6.2. Define API security requirements and access controls | 3
Detailed Design - Component Design | Component A Design | 6.3. Document API contracts and usage guidelines | 3
Detailed Design - Component Design | Component A Design | 6.4. Coordinate API design with other teams | 2
Detailed Design - Component Design | Component A Design | 6.5. Ensure API design adheres to RESTful principles | 2
Detailed Design - Component Design | Component A Design | 7.1. Design input validation and error handling strategies | 3
Detailed Design - Component Design | Component A Design | 7.2. Identify potential input validation requirements | 2
Detailed Design - Component Design | Component A Design | 7.3. Specify error codes and error message formats | 3
Detailed Design - Component Design | Component A Design | 7.4. Document error handling processes and user notifications | 3
Detailed Design - Component Design | Component A Design | 7.5. Define fallback mechanisms in case of failures | 2
Detailed Design - Component Design | Component A Design | 8.1. Develop detailed UML diagrams for the component | 5
Detailed Design - Component Design | Component A Design | 8.2. Create class diagrams to depict component structure | 3
Detailed Design - Component Design | Component A Design | 8.3. Generate sequence diagrams to illustrate interactions | 3
Detailed Design - Component Design | Component A Design | 8.4. Produce state diagrams for component behavior | 3
Detailed Design - Component Design | Component A Design | 8.5. Design deployment diagrams for component deployment | 3
Detailed Design - Component Design | Component A Design | 9.1. Review the design with front-end developers for input | 3
Detailed Design - Component Design | Component A Design | 9.2. Seek input on UI/UX considerations and user interaction | 3
Detailed Design - Component Design | Component A Design | 9.3. Incorporate front-end team's suggestions and feedback | 3
Detailed Design - Component Design | Component A Design | 9.4. Ensure alignment of UI components with design | 2
Detailed Design - Component Design | Component A Design | 9.5. Verify the responsiveness and usability of the design | 2
Detailed Design - Component Design | Component A Design | 10.1. Document the finalized component design | 3
Detailed Design - Component Design | Component A Design | 10.2. Create comprehensive design documentation | 2
Detailed Design - Component Design | Component A Design | 10.3. Include design rationale decisions and considerations | 3
Detailed Design - Component Design | Component A Design | 10.4. Prepare design artifacts for knowledge sharing | 2
Detailed Design - Component Design | Component A Design | 10.5. Archive design documentation for future reference | 2
Detailed Design - Component Design | Component A Design | 11.1. Validate the design by creating a prototype | 4
Detailed Design - Component Design | Component A Design | 11.2. Build a functional prototype of the component | 3
Detailed Design - Component Design | Component A Design | 11.3. Test the prototype against design requirements | 3
Detailed Design - Component Design | Component A Design | 11.4. Gather user feedback on prototype usability | 3
Detailed Design - Component Design | Component A Design | 11.5. Iterate on the design based on prototype testing | 3
Detailed Design - Component Design | Component A Design | 12.1. Present the component design to stakeholders for approval | 2
Detailed Design - Component Design | Component A Design | 12.2. Schedule a design review meeting with stakeholders | 3
Detailed Design - Component Design | Component A Design | 12.3. Prepare a comprehensive presentation | 2
Detailed Design - Component Design | Component A Design | 12.4. Address stakeholders' questions and concerns | 3
Detailed Design - Component Design | Component A Design | 12.5. Obtain formal approval and sign-off | 2

## Development
Phase | Story | Sub-Task | Story Points
Development | Sub-API 1 - Feature 1 Implementation | 1.1. Set up the development environment | 2
Development | Sub-API 1 - Feature 1 Implementation | 1.2. Create a new branch in the version control system | 2
Development | Sub-API 1 - Feature 1 Implementation | 1.3. Implement the core functionality of Feature 1 | 8
Development | Sub-API 1 - Feature 1 Implementation | 1.4. Write unit tests for Feature 1 | 4
Development | Sub-API 1 - Feature 1 Implementation | 1.5. Debug and fix any issues in the initial implementation | 6
Development | Sub-API 1 - Feature 1 Implementation | 1.6. Optimize the code for performance | 6
Development | Sub-API 1 - Feature 1 Implementation | 1.7. Conduct code reviews with team members | 4
Development | Sub-API 1 - Feature 1 Implementation | 1.8. Address code review feedback and make necessary changes | 4
Development | Sub-API 1 - Feature 1 Implementation | 1.9. Ensure coding standards and best practices are followed | 3
Development | Sub-API 1 - Feature 1 Implementation | 1.10. Update documentation for Feature 1 | 3
Development | Sub-API 1 - Feature 1 Implementation | 1.11. Merge the feature branch into the main development branch | 2
Development | Sub-API 1 - Feature 1 Implementation | 1.12. Verify integration with other components | 4
Development | Sub-API 1 - Feature 1 Implementation | 1.13. Update the test suite to include Feature 1 | 3
Development | Sub-API 1 - Feature 1 Implementation | 1.14. Conduct regression testing | 5
Development | Sub-API 1 - Feature 1 Implementation | 1.15. Address and resolve any regression issues | 4
Development | Sub-API 1 - Feature 1 Implementation | 1.16. Update user documentation for Feature 1 | 3
Development | Sub-API 1 - Feature 1 Implementation | 1.17. Prepare for deployment | 3
Development | Sub-API 1 - Feature 1 Implementation | 1.18. Deploy Feature 1 to the staging environment | 4
Development | Sub-API 1 - Feature 1 Implementation | 1.19. Perform testing in the staging environment | 5
Development | Sub-API 1 - Feature 1 Implementation | 1.20. Address any staging environment issues | 4
Development | Sub-API 1 - Feature 1 Implementation | 1.21. Obtain stakeholder approval for Feature 1 | 2
Development | Sub-API 1 - Feature 1 Implementation | 1.22. Deploy Feature 1 to the production environment | 4
Development | Sub-API 1 - Feature 1 Implementation | 1.23. Conduct post-deployment testing | 4
Development | Sub-API 1 - Feature 1 Implementation | 1.24. Monitor production for any issues or performance bottlenecks | 4
Development | Sub-API 1 - Feature 1 Implementation | 1.25. Provide support for end-users and address any reported issues | 5
Development | Sub-API 2 - Feature 1 Implementation | 1.1. Set up the development environment | 2
Development | Sub-API 2 - Feature 1 Implementation | 1.2. Create a new branch in the version control system | 2
Development | Sub-API 2 - Feature 1 Implementation | 1.3. Implement the core functionality of Feature 1 | 8
Development | Sub-API 2 - Feature 1 Implementation | 1.4. Write unit tests for Feature 1 | 4
Development | Sub-API 2 - Feature 1 Implementation | 1.5. Debug and fix any issues in the initial implementation | 6
Development | Sub-API 2 - Feature 1 Implementation | 1.6. Optimize the code for performance | 6
Development | Sub-API 2 - Feature 1 Implementation | 1.7. Conduct code reviews with team members | 4
Development | Sub-API 2 - Feature 1 Implementation | 1.8. Address code review feedback and make necessary changes | 4
Development | Sub-API 2 - Feature 1 Implementation | 1.9. Ensure coding standards and best practices are followed | 3
Development | Sub-API 2 - Feature 1 Implementation | 1.10. Update documentation for Feature 1 | 3
Development | Sub-API 2 - Feature 1 Implementation | 1.11. Merge the feature branch into the main development branch | 2
Development | Sub-API 2 - Feature 1 Implementation | 1.12. Verify integration with other components | 4
Development | Sub-API 2 - Feature 1 Implementation | 1.13. Update the test suite to include Feature 1 | 3
Development | Sub-API 2 - Feature 1 Implementation | 1.14. Conduct regression testing | 5
Development | Sub-API 2 - Feature 1 Implementation | 1.15. Address and resolve any regression issues | 4
Development | Sub-API 2 - Feature 1 Implementation | 1.16. Update user documentation for Feature 1 | 3
Development | Sub-API 2 - Feature 1 Implementation | 1.17. Prepare for deployment | 3
Development | Sub-API 2 - Feature 1 Implementation | 1.18. Deploy Feature 1 to the staging environment | 4
Development | Sub-API 2 - Feature 1 Implementation | 1.19. Perform testing in the staging environment | 5
Development | Sub-API 2 - Feature 1 Implementation | 1.20. Address any staging environment issues | 4
Development | Sub-API 2 - Feature 1 Implementation | 1.21. Obtain stakeholder approval for Feature 1 | 2
Development | Sub-API 2 - Feature 1 Implementation | 1.22. Deploy Feature 1 to the production environment | 4
Development | Sub-API 2 - Feature 1 Implementation | 1.23. Conduct post-deployment testing | 4
Development | Sub-API 2 - Feature 1 Implementation | 1.24. Monitor production for any issues or performance bottlenecks | 4
Development | Sub-API 2 - Feature 1 Implementation | 1.25. Provide support for end-users and address any reported issues | 5
Development | Sub-API 3 - Feature 1 Implementation | 1.1. Set up the development environment | 2
Development | Sub-API 3 - Feature 1 Implementation | 1.2. Create a new branch in the version control system | 2
Development | Sub-API 3 - Feature 1 Implementation | 1.3. Implement the core functionality of Feature 1 | 8
Development | Sub-API 3 - Feature 1 Implementation | 1.4. Write unit tests for Feature 1 | 4
Development | Sub-API 3 - Feature 1 Implementation | 1.5. Debug and fix any issues in the initial implementation | 6
Development | Sub-API 3 - Feature 1 Implementation | 1.6. Optimize the code for performance | 6
Development | Sub-API 3 - Feature 1 Implementation | 1.7. Conduct code reviews with team members | 4
Development | Sub-API 3 - Feature 1 Implementation | 1.8. Address code review feedback and make necessary changes | 4
Development | Sub-API 3 - Feature 1 Implementation | 1.9. Ensure coding standards and best practices are followed | 3
Development | Sub-API 3 - Feature 1 Implementation | 1.10. Update documentation for Feature 1 | 3
Development | Sub-API 3 - Feature 1 Implementation | 1.11. Merge the feature branch into the main development branch | 2
Development | Sub-API 3 - Feature 1 Implementation | 1.12. Verify integration with other components | 4
Development | Sub-API 3 - Feature 1 Implementation | 1.13. Update the test suite to include Feature 1 | 3
Development | Sub-API 3 - Feature 1 Implementation | 1.14. Conduct regression testing | 5
Development | Sub-API 3 - Feature 1 Implementation | 1.15. Address and resolve any regression issues | 4
Development | Sub-API 3 - Feature 1 Implementation | 1.16. Update user documentation for Feature 1 | 3
Development | Sub-API 3 - Feature 1 Implementation | 1.17. Prepare for deployment | 3
Development | Sub-API 3 - Feature 1 Implementation | 1.18. Deploy Feature 1 to the staging environment | 4
Development | Sub-API 3 - Feature 1 Implementation | 1.19. Perform testing in the staging environment | 5
Development | Sub-API 3 - Feature 1 Implementation | 1.20. Address any staging environment issues | 4
Development | Sub-API 3 - Feature 1 Implementation | 1.21. Obtain stakeholder approval for Feature 1 | 2
Development | Sub-API 3 - Feature 1 Implementation | 1.22. Deploy Feature 1 to the production environment | 4
Development | Sub-API 3 - Feature 1 Implementation | 1.23. Conduct post-deployment testing | 4
Development | Sub-API 3 - Feature 1 Implementation | 1.24. Monitor production for any issues or performance bottlenecks | 4
Development | Sub-API 3 - Feature 1 Implementation | 1.25. Provide support for end-users and address any reported issues | 5
Development | Sub-API 4 - Feature 1 Implementation | 1.1. Set up the development environment | 2
Development | Sub-API 4 - Feature 1 Implementation | 1.2. Create a new branch in the version control system | 2
Development | Sub-API 4 - Feature 1 Implementation | 1.3. Implement the core functionality of Feature 1 | 8
Development | Sub-API 4 - Feature 1 Implementation | 1.4. Write unit tests for Feature 1 | 4
Development | Sub-API 4 - Feature 1 Implementation | 1.5. Debug and fix any issues in the initial implementation | 6
Development | Sub-API 4 - Feature 1 Implementation | 1.6. Optimize the code for performance | 6
Development | Sub-API 4 - Feature 1 Implementation | 1.7. Conduct code reviews with team members | 4
Development | Sub-API 4 - Feature 1 Implementation | 1.8. Address code review feedback and make necessary changes | 4
Development | Sub-API 4 - Feature 1 Implementation | 1.9. Ensure coding standards and best practices are followed | 3
Development | Sub-API 4 - Feature 1 Implementation | 1.10. Update documentation for Feature 1 | 3
Development | Sub-API 4 - Feature 1 Implementation | 1.11. Merge the feature branch into the main development branch | 2
Development | Sub-API 4 - Feature 1 Implementation | 1.12. Verify integration with other components | 4
Development | Sub-API 4 - Feature 1 Implementation | 1.13. Update the test suite to include Feature 1 | 3
Development | Sub-API 4 - Feature 1 Implementation | 1.14. Conduct regression testing | 5
Development | Sub-API 4 - Feature 1 Implementation | 1.15. Address and resolve any regression issues | 4
Development | Sub-API 4 - Feature 1 Implementation | 1.16. Update user documentation for Feature 1 | 3
Development | Sub-API 4 - Feature 1 Implementation | 1.17. Prepare for deployment | 3
Development | Sub-API 4 - Feature 1 Implementation | 1.18. Deploy Feature 1 to the staging environment | 4
Development | Sub-API 4 - Feature 1 Implementation | 1.19. Perform testing in the staging environment | 5
Development | Sub-API 4 - Feature 1 Implementation | 1.20. Address any staging environment issues | 4
Development | Sub-API 4 - Feature 1 Implementation | 1.21. Obtain stakeholder approval for Feature 1 | 2
Development | Sub-API 4 - Feature 1 Implementation | 1.22.00 Deploy Feature 1 to the production environment | 4
Development | Sub-API 4 - Feature 1 Implementation | 1.23. Conduct post-deployment testing | 4
Development | Sub-API 4 - Feature 1 Implementation | 1.24. Monitor production for any issues or performance bottlenecks | 4
Development | Sub-API 4 - Feature 1 Implementation | 1.25. Provide support for end-users and address any reported issues | 5
Development | Sub-API 5 - Feature 1 Implementation | 1.1. Set up the development environment | 2
Development | Sub-API 5 - Feature 1 Implementation | 1.2. Create a new branch in the version control system | 2
Development | Sub-API 5 - Feature 1 Implementation | 1.3. Implement the core functionality of Feature 1 | 8
Development | Sub-API 5 - Feature 1 Implementation | 1.4. Write unit tests for Feature 1 | 4
Development | Sub-API 5 - Feature 1 Implementation | 1.5. Debug and fix any issues in the initial implementation | 6
Development | Sub-API 5 - Feature 1 Implementation | 1.6. Optimize the code for performance | 6
Development | Sub-API 5 - Feature 1 Implementation | 1.7. Conduct code reviews with team members | 4
Development | Sub-API 5 - Feature 1 Implementation | 1.8. Address code review feedback and make necessary changes | 4
Development | Sub-API 5 - Feature 1 Implementation | 1.9. Ensure coding standards and best practices are followed | 3
Development | Sub-API 5 - Feature 1 Implementation | 1.10. Update documentation for Feature 1 | 3
Development | Sub-API 5 - Feature 1 Implementation | 1.11. Merge the feature branch into the main development branch | 2
Development | Sub-API 5 - Feature 1 Implementation | 1.12. Verify integration with other components | 4
Development | Sub-API 5 - Feature 1 Implementation | 1.13. Update the test suite to include Feature 1 | 3
Development | Sub-API 5 - Feature 1 Implementation | 1.14. Conduct regression testing | 5
Development | Sub-API 5 - Feature 1 Implementation | 1.15. Address and resolve any regression issues | 4
Development | Sub-API 5 - Feature 1 Implementation | 1.16. Update user documentation for Feature 1 | 3
Development | Sub-API 5 - Feature 1 Implementation | 1.17. Prepare for deployment | 3
Development | Sub-API 5 - Feature 1 Implementation | 1.18. Deploy Feature 1 to the staging environment | 4
Development | Sub-API 5 - Feature 1 Implementation | 1.19. Perform testing in the staging environment | 5
Development | Sub-API 5 - Feature 1 Implementation | 1.20. Address any staging environment issues | 4
Development | Sub-API 5 - Feature 1 Implementation | 1.21. Obtain stakeholder approval for Feature 1 | 2
Development | Sub-API 5 - Feature 1 Implementation | 1.22. Deploy Feature 1 to the production environment | 4
Development | Sub-API 5 - Feature 1 Implementation | 1.23. Conduct post-deployment testing | 4
Development | Sub-API 5 - Feature 1 Implementation | 1.24. Monitor production for any issues or performance bottlenecks | 4
Development | Sub-API 5 - Feature 1 Implementation | 1.25. Provide support for end-users and address any reported issues | 5

## Code Review
Phase | Story | Sub-Task | Story Points
Code Review | Sub-API 1 - Feature 1 Code Review | 1.1. Review code changes related to Feature 1 | 5
Code Review | Sub-API 1 - Feature 2 Code Review | 1.2. Review code changes related to Feature 2 | 5
Code Review | Sub-API 1 - Feature 3 Code Review | 1.3. Review code changes related to Feature 3 | 5
Code Review | Sub-API 1 - Feature 4 Code Review | 1.4. Review code changes related to Feature 4 | 5
Code Review | Sub-API 1 - Feature 5 Code Review | 1.5. Review code changes related to Feature 5 | 5
Code Review | Sub-API 1 - Feature 6 Code Review | 1.6. Review code changes related to Feature 6 | 5
Code Review | Sub-API 1 - Feature 7 Code Review | 1.7. Review code changes related to Feature 7 | 5
Code Review | Sub-API 1 - Feature 8 Code Review | 1.8. Review code changes related to Feature 8 | 5
Code Review | Sub-API 1 - Feature 9 Code Review | 1.9. Review code changes related to Feature 9 | 5
Code Review | Sub-API 1 - Feature 10 Code Review | 1.10. Review code changes related to Feature 10 | 5
Code Review | Sub-API 1 - Feature 11 Code Review | 1.11. Review code changes related to Feature 11 | 5
Code Review | Sub-API 1 - Feature 12 Code Review | 1.12. Review code changes related to Feature 12 | 5
Code Review | Sub-API 1 - Feature 13 Code Review | 1.13. Review code changes related to Feature 13 | 5
Code Review | Sub-API 1 - Feature 14 Code Review | 1.14. Review code changes related to Feature 14 | 5
Code Review | Sub-API 1 - Feature 15 Code Review | 1.15. Review code changes related to Feature 15 | 5
Code Review | Sub-API 1 - Feature 16 Code Review | 1.16. Review code changes related to Feature 16 | 5
Code Review | Sub-API 1 - Feature 17 Code Review | 1.17. Review code changes related to Feature 17 | 5
Code Review | Sub-API 1 - Feature 18 Code Review | 1.18. Review code changes related to Feature 18 | 5
Code Review | Sub-API 1 - Feature 19 Code Review | 1.19. Review code changes related to Feature 19 | 5
Code Review | Sub-API 1 - Feature 20 Code Review | 1.20. Review code changes related to Feature 20 | 5
Code Review | Sub-API 2 - Feature 1 Code Review | 1.1. Review code changes related to Feature 1 | 5
Code Review | Sub-API 2 - Feature 2 Code Review | 1.2. Review code changes related to Feature 2 | 5
Code Review | Sub-API 2 - Feature 3 Code Review | 1.3. Review code changes related to Feature 3 | 5
Code Review | Sub-API 2 - Feature 4 Code Review | 1.4. Review code changes related to Feature 4 | 5
Code Review | Sub-API 2 - Feature 5 Code Review | 1.5. Review code changes related to Feature 5 | 5
Code Review | Sub-API 2 - Feature 6 Code Review | 1.6. Review code changes related to Feature 6 | 5
Code Review | Sub-API 2 - Feature 7 Code Review | 1.7. Review code changes related to Feature 7 | 5
Code Review | Sub-API 2 - Feature 8 Code Review | 1.8. Review code changes related to Feature 8 | 5
Code Review | Sub-API 2 - Feature 9 Code Review | 1.9. Review code changes related to Feature 9 | 5
Code Review | Sub-API 2 - Feature 10 Code Review | 1.10. Review code changes related to Feature 10 | 5
Code Review | Sub-API 2 - Feature 11 Code Review | 1.11. Review code changes related to Feature 11 | 5
Code Review | Sub-API 2 - Feature 12 Code Review | 1.12. Review code changes related to Feature 12 | 5
Code Review | Sub-API 2 - Feature 13 Code Review | 1.13. Review code changes related to Feature 13 | 5
Code Review | Sub-API 2 - Feature 14 Code Review | 1.14. Review code changes related to Feature 14 | 5
Code Review | Sub-API 2 - Feature 15 Code Review | 1.15. Review code changes related to Feature 15 | 5
Code Review | Sub-API 2 - Feature 16 Code Review | 1.16. Review code changes related to Feature 16 | 5
Code Review | Sub-API 2 - Feature 17 Code Review | 1.17. Review code changes related to Feature 17 | 5
Code Review | Sub-API 2 - Feature 18 Code Review | 1.18. Review code changes related to Feature 18 | 5
Code Review | Sub-API 2 - Feature 19 Code Review | 1.19. Review code changes related to Feature 19 | 5
Code Review | Sub-API 2 - Feature 20 Code Review | 1.20. Review code changes related to Feature 20 | 5
Code Review | Sub-API 3 - Feature 1 Code Review | 1.1. Review code changes related to Feature 1 | 5
Code Review | Sub-API 3 - Feature 2 Code Review | 1.2. Review code changes related to Feature 2 | 5
Code Review | Sub-API 3 - Feature 3 Code Review | 1.3. Review code changes related to Feature 3 | 5
Code Review | Sub-API 3 - Feature 4 Code Review | 1.4. Review code changes related to Feature 4 | 5
Code Review | Sub-API 3 - Feature 5 Code Review | 1.5. Review code changes related to Feature 5 | 5
Code Review | Sub-API 3 - Feature 6 Code Review | 1.6. Review code changes related to Feature 6 | 5
Code Review | Sub-API 3 - Feature 7 Code Review | 1.7. Review code changes related to Feature 7 | 5
Code Review | Sub-API 3 - Feature 8 Code Review | 1.8. Review code changes related to Feature 8 | 5
Code Review | Sub-API 3 - Feature 9 Code Review | 1.9. Review code changes related to Feature 9 | 5
Code Review | Sub-API 3 - Feature 10 Code Review | 1.10. Review code changes related to Feature 10 | 5
Code Review | Sub-API 3 - Feature 11 Code Review | 1.11. Review code changes related to Feature 11 | 5
Code Review | Sub-API 3 - Feature 12 Code Review | 1.12. Review code changes related to Feature 12 | 5
Code Review | Sub-API 3 - Feature 13 Code Review | 1.13. Review code changes related to Feature 13 | 5
Code Review | Sub-API 3 - Feature 14 Code Review | 1.14. Review code changes related to Feature 14 | 5
Code Review | Sub-API 3 - Feature 15 Code Review | 1.15. Review code changes related to Feature 15 | 5
Code Review | Sub-API 3 - Feature 16 Code Review | 1.16. Review code changes related to Feature 16 | 5
Code Review | Sub-API 3 - Feature 17 Code Review | 1.17. Review code changes related to Feature 17 | 5
Code Review | Sub-API 3 - Feature 18 Code Review | 1.18. Review code changes related to Feature 18 | 5
Code Review | Sub-API 3 - Feature 19 Code Review | 1.19. Review code changes related to Feature 19 | 5
Code Review | Sub-API 3 - Feature 20 Code Review | 1.20. Review code changes related to Feature 20 | 5
Code Review | Sub-API 4 - Feature 1 Code Review | 1.1. Review code changes related to Feature 1 | 5
Code Review | Sub-API 4 - Feature 2 Code Review | 1.2. Review code changes related to Feature 2 | 5
Code Review | Sub-API 4 - Feature 3 Code Review | 1.3. Review code changes related to Feature 3 | 5
Code Review | Sub-API 4 - Feature 4 Code Review | 1.4. Review code changes related to Feature 4 | 5
Code Review | Sub-API 4 - Feature 5 Code Review | 1.5. Review code changes related to Feature 5 | 5
Code Review | Sub-API 4 - Feature 6 Code Review | 1.6. Review code changes related to Feature 6 | 5
Code Review | Sub-API 4 - Feature 7 Code Review | 1.7. Review code changes related to Feature 7 | 5
Code Review | Sub-API 4 - Feature 8 Code Review | 1.8. Review code changes related to Feature 8 | 5
Code Review | Sub-API 4 - Feature 9 Code Review | 1.9. Review code changes related to Feature 9 | 5
Code Review | Sub-API 4 - Feature 10 Code Review | 1.10. Review code changes related to Feature 10 | 5
Code Review | Sub-API 4 - Feature 11 Code Review | 1.11. Review code changes related to Feature 11 | 5
Code Review | Sub-API 4 - Feature 12 Code Review | 1.12. Review code changes related to Feature 12 | 5
Code Review | Sub-API 4 - Feature 13 Code Review | 1.13. Review code changes related to Feature 13 | 5
Code Review | Sub-API 4 - Feature 14 Code Review | 1.14. Review code changes related to Feature 14 | 5
Code Review | Sub-API 4 - Feature 15 Code Review | 1.15. Review code changes related to Feature 15 | 5
Code Review | Sub-API 4 - Feature 16 Code Review | 1.16. Review code changes related to Feature 16 | 5
Code Review | Sub-API 4 - Feature 17 Code Review | 1.17. Review code changes related to Feature 17 | 5
Code Review | Sub-API 4 - Feature 18 Code Review | 1.18. Review code changes related to Feature 18 | 5
Code Review | Sub-API 4 - Feature 19 Code Review | 1.19. Review code changes related to Feature 19 | 5
Code Review | Sub-API 4 - Feature 20 Code Review | 1.20. Review code changes related to Feature 20 | 5
Code Review | Sub-API 5 - Feature 1 Code Review | 1.1. Review code changes related to Feature 1 | 5
Code Review | Sub-API 5 - Feature 2 Code Review | 1.2. Review code changes related to Feature 2 | 5
Code Review | Sub-API 5 - Feature 3 Code Review | 1.3. Review code changes related to Feature 3 | 5
Code Review | Sub-API 5 - Feature 4 Code Review | 1.4. Review code changes related to Feature 4 | 5
Code Review | Sub-API 5 - Feature 5 Code Review | 1.5. Review code changes related to Feature 5 | 5
Code Review | Sub-API 5 - Feature 6 Code Review | 1.6. Review code changes related to Feature 6 | 5
Code Review | Sub-API 5 - Feature 7 Code Review | 1.7. Review code changes related to Feature 7 | 5
Code Review | Sub-API 5 - Feature 8 Code Review | 1.8. Review code changes related to Feature 8 | 5
Code Review | Sub-API 5 - Feature 9 Code Review | 1.9. Review code changes related to Feature 9 | 5
Code Review | Sub-API 5 - Feature 10 Code Review | 1.10. Review code changes related to Feature 10 | 5
Code Review | Sub-API 5 - Feature 11 Code Review | 1.11. Review code changes related to Feature 11 | 5
Code Review | Sub-API 5 - Feature 12 Code Review | 1.12. Review code changes related to Feature 12 | 5
Code Review | Sub-API 5 - Feature 13 Code Review | 1.13. Review code changes related to Feature 13 | 5
Code Review | Sub-API 5 - Feature 14 Code Review | 1.14. Review code changes related to Feature 14 | 5
Code Review | Sub-API 5 - Feature 15 Code Review | 1.15. Review code changes related to Feature 15 | 5
Code Review | Sub-API 5 - Feature 16 Code Review | 1.16. Review code changes related to Feature 16 | 5
Code Review | Sub-API 5 - Feature 17 Code Review | 1.17. Review code changes related to Feature 17 | 5
Code Review | Sub-API 5 - Feature 18 Code Review | 1.18. Review code changes related to Feature 18 | 5
Code Review | Sub-API 5 - Feature 19 Code Review | 1.19. Review code changes related to Feature 19 | 5
Code Review | Sub-API 5 - Feature 20 Code Review | 1.20. Review code changes related to Feature 20 | 5